## Sheet1
Critical Path & Project Duration
The Critical Path (one of the longest paths) is:
A → D → H → I → J → K → L → N
(Duration = 33 days)
So, the minimum time to complete the project = 33 days (based on the last task end day).
Why this is the critical path?
It has the longest duration.
Any delay in these tasks will delay the whole project.
Other tasks (like B, C, E, F, G, M) have float time (can be delayed without affecting the total duration).