## Task Identification
Task ID | Task Name | Start Day | End Day | Duration | Predecessor | Gantt Chart
A | System Requirements | 1 | 2 | 2 | -
B | Feasibility Study | 1 | 3 | 3 | -
C | Project Methodology | 4 | 4 | 1 | B
D | Time Estimation | 5 | 5 | 1 | A , C
E | Task Identification | 6 | 6 | 1 | D
F | PERT Chart | 7 | 7 | 1 | E
G | Gantt Chart | 8 | 8 | 1 | E
H | System Analysis | 9 | 12 | 4 | D
I | System Design | 13 | 17 | 5 | H
J | Database Design | 18 | 21 | 4 | I
K | System Development | 22 | 31 | 10 | J
L | System Testing | 32 | 36 | 5 | K
M | Documentation | 32 | 35 | 4 | K
N | Final Review | 37 | 38 | 2 | L , M